|  | ΟΡΓΑΝΙΣΜΟΣ ΛΙΜΕΝΟΣ ΠΕΙΡΑΙΩΣ Α.Ε. Ακτή Μιαούλη 10, 185 38 Πειραιάς |
| --- | --- |

Πρόχειρος Διαγωνισμός με κλειστές προσφορές

για την επιλογή Εξωτερικού Συνεργάτη από το ‘Μητρώο Εξωτερικών Συνεργατών για την  υλοποίηση Δράσεων Ευρωπαϊκών Έργων και Προγραμμάτων, που συμμετέχει η ΟΛΠ ΑΕ  με σκοπό την συμμετοχή του στην τεχνική υλοποίηση του Ευρωπαϊκού Έργου:

Ημερομηνία Διενέργειας  Διαγωνισμού 20/04/2022

## ΣΥΝΟΠΤΙΚΑ ΣΤΟΙΧΕΙΑ ΕΡΓΟΥ

| ΑΝΑΘΕΤΩΝ ΦΟΡΕΑΣ | ΟΡΓΑΝΙΣΜΟΣ ΛΙΜΕΝΟΣ ΠΕΙΡΑΙΩΣ Α.Ε. (ΟΛΠ Α.Ε.) |
| --- | --- |
| ΑΝΤΙΚΕΙΜΕΝΟ ΤΟΥ ΔΙΑΓΩΝΙΣΜΟΥ | Επιλογή Εξωτερικού Συνεργάτη από το ‘Μητρώο Εξωτερικών Συνεργατών για την υλοποίηση Δράσεων Ευρωπαϊκών Έργων και Προγραμμάτων, που συμμετέχει η ΟΛΠ ΑΕ με σκοπό την συμμετοχή του στην τεχνική υλοποίηση του Ευρωπαϊκού Έργου “ARSINOE - Climate resilient regions through systemic solutions and innovations” |
| ΕΡΓΟ | Συμμετοχή Εξωτερικού Συνεργάτη στην υλοποίηση των τεχνικών δράσεων του Ευρωπαϊκού έργου “ARSINOE” |
| ΠΡΟΫΠΟΛΟΓΙΣΜΟΣ | ______________ |
| ΚΑΤΑΛΗΚΤΙΚΗ ΗΜΕΡΟΜΗΝΙΑ ΥΠΟΒΟΛΗΣ ΠΡΟΣΦΟΡΩΝ | 05 /05/2022 και ώρα 14:00 |
| ΠΛΗΡΟΦΟΡΙΕΣ | procurement@olp.gr |

### ΑΝΤΙΚΕΙΜΕΝΟ ΤΟΥ ΔΙΑΓΩΝΙΣΜΟΥ

Αντικείμενο του παρόντος διαγωνισμού είναι η επιλογή Εξωτερικού Συνεργάτη από το Μητρώο Εξωτερικών Συνεργατών για την υλοποίηση Δράσεων Ευρωπαϊκών Έργων και Προγραμμάτων, που συμμετέχει η ΟΛΠ ΑΕ  με σκοπό την συμμετοχή του στην υλοποίηση των τεχνικών δράσεων του Ευρωπαϊκού Έργου: “ ARSINOE - Climate resilient regions through systemic solutions and innovations”  στο πλαίσιο του προγράμματος HORIZON 2020.

### ΠΕΡΙΓΡΑΦΗ ΤΟΥ ΕΡΓΟΥ ARSINOE

Αναγνωρίζοντας ότι η κλιματική αλλαγή είναι περίπλοκη και συνδέεται στενά με άλλες παγκόσμιες προκλήσεις, όπως η επισιτιστική ασφάλεια, η λειψυδρία, η εξάντληση της βιοποικιλότητας και η υποβάθμιση του περιβάλλοντος, γίνεται αντιληπτό ότι δεν αρκεί η χρήση παραδοσιακών προσεγγίσεων για την καινοτομία οι οποίες εστιάζουν μόνο σε μία πτυχή του προβλήματος. Το έργο «ARSINOE - Περιφέρειες ανθεκτικές στο κλίμα μέσω συστημικών λύσεων και καινοτομιών», συγχρηματοδοτούμενο από το πρόγραμμα Horizon 2020 επιδιώκει να διαμορφώσει νέους δρόμους προς την ανθεκτικότητα παρέχοντας περιφερειακά πακέτα καινοτομίας που δημιουργούν ένα οικοσύστημα για την ανάπτυξη και εφαρμογή καινοτόμων μέτρων και λύσεων προσαρμογής στην κλιματική αλλαγή σε όλη την Ευρώπη.

Η προσέγγιση καινοτομίας συστημάτων (SIA) αντιμετωπίζει την αυξανόμενη πολυπλοκότητα, τις αλληλεξαρτήσεις και τη διασύνδεση των σύγχρονων κοινωνιών και οικονομιών, εστιάζοντας στις λειτουργίες του διατομεακού συστήματος στο σύνολό του καθώς και στην ποικιλία των εμπλεκομένων φορέων. Το παράθυρο καινοτομίας για το κλίμα (CIW) είναι η αγορά καινοτομιών αναφοράς της ΕΕ για τις τεχνολογίες προσαρμογής στην κλιματική αλλαγή. Το έργο ARSINOE διαμορφώνει τρόπους ανθεκτικότητας φέρνοντας σε επαφή τη SIA και την CIW, για να χτίσει ένα οικοσύστημα για λύσεις προσαρμογής στην κλιματική αλλαγή.

Εντός του οικοσυστήματος ARSINOE, οι τρόποι για λύσεις συνδημιουργούνται και σχεδιάζονται από κοινού από τα ενδιαφερόμενα μέρη, τα οποία μπορούν στη συνέχεια να επιλέξουν είτε υπάρχουσες τεχνολογίες CIW, είτε τεχνολογίες από νέους παρόχους (ή συνδυασμό τους) για τη δημιουργία δέσμης μέτρων καινοτομίας.

Η δέσμη αυτή των μέτρων μπορεί να έχει σχεδιαστεί για εφαρμογή σε συγκεκριμένη περιοχή, αλλά τα δομικά στοιχεία της είναι μεταβιβάσιμα και επαναχρησιμοποιήσιμα και μπορούν να προσαρμοστούν και να ενημερωθούν εκ νέου. Με τον τρόπο αυτό, ο χρήστης (περιοχή) λαμβάνει ένα πακέτο καινοτομίας που αποτελείται από επικυρωμένες τεχνολογίες (επέκταση της αγοράς για ciw), ενώ οι νέες τεχνολογίες που εφαρμόζονται στο συγκεκριμένο τοπικό πακέτο καινοτομίας έχουν την ευκαιρία να επικυρωθούν και να γίνουν μέλη στο CIW, ενώ η κοινωνία (πολίτες, ενδιαφερόμενοι φορείς) επωφελείται στο σύνολό της. Το ARSINOE εφαρμόζει μια προσέγγιση τριών επιπέδων: α) με τη χρήση του SIA ενσωματώνει πολύπλευρες τεχνολογικές, ψηφιακές, επιχειρηματικές, διακυβέρνηση και περιβαλλοντικές πτυχές με την κοινωνική καινοτομία για την ανάπτυξη τρόπων προσαρμογής στην κλιματική αλλαγή για συγκεκριμένες περιφέρειες, β) συνδέεται με την CIW για τη δημιουργία πακέτων καινοτομίας, ταιριάζοντας τις καινοτομίες με τελικούς χρήστες/περιφέρειες, γ) προωθεί τη βιωσιμότητα και την ανάπτυξη του οικοσυστήματος μέσω της διασταύρωσης και αναπαραγωγής σε όλες τις περιφέρειες και διάφορες βαθμίδες σε ευρωπαϊκό επίπεδο και πέραν αυτής, χρησιμοποιώντας συγκεκριμένα επιχειρηματικά μοντέλα, δράσεις αξιοποίησης και προβολής. Η προσέγγιση του έργου ARSINOE παρουσιάζεται σε εννέα ευρέως ποικίλους πιλοτικούς προορισμούς, με σκοπό την τεκμηρίωση στην δυνατότητα εφαρμογής, την δυνατότητα αναπαραγωγής, την δυναμική και την αποτελεσματικότητά της.

### ΠΕΡΙΓΡΑΦΗ ΤΟΥ ΕΡΓΟΥ ΤΟΥ ΣΥΝΕΡΓΑΤΗ

Ο σκοπός της δράσης είναι η συμμετοχή του εξωτερικού συνεργάτη στην υποβοήθηση  της συμμετοχής του ΟΛΠ στο έργο έργα “ARSINOE και στην υλοποίηση των τεχνικών δράσεων όπως αυτές προβλέπονται στο σχετικό Συμφωνητικό Επιχορήγησης του έργου. Ο ΟΛΠ Α.Ε. συμμετέχει στα παρακάτω Πακέτα Εργασίας.

Στο Πακέτο Εργασίας 2, η συστημική καινοτομία βρίσκεται στον πυρήνα της μεθοδολογίας για την επίλυση σύνθετων προβλημάτων πολλαπλών παραμέτρων. Η προτεινόμενη μέθοδος συμβάλλει στην προσέγγιση της καινοτομίας του ARSINOE, ενώ δίδεται έμφαση στις λειτουργίες του διατομεακού συστήματος «στο σύνολό του» και στην ποικιλία των παραγόντων. Το πλαίσιο και οι λύσεις για την αντιμετώπιση της κλιματικής αλλαγής θα εντοπιστούν μέσω ποιοτικής ανάλυσης, συνεντεύξεων και εργαστηρίων με σκοπό τον κοινό σχεδιασμό ενός αποδεκτού οράματος για το μέλλον και τον προσδιορισμό τρόπων επίτευξης των στόχων.

Το Πακέτο Εργασίας 5 επικεντρώνεται σε πέντε κύριες δραστηριότητες: i) ανοικτός διαγωνισμός καινοτομίας (Innovation Bazaar), ii) ανάπτυξη μεθοδολογιών αξιολόγησης, κριτηρίων επιλογής, iii) κλιματικό πλαίσιο που θα επιλεγεί με γνώμονα τη ζήτηση, iv) επιχειρηματικά μοντέλα και συμβάσεις αγοράς v) πρόβλεψη / αναπαραγωγή της αγοράς

Στο Πακέτο Εργασίας 6 παρουσιάζονται 9 διαφορετικές και συμπληρωματικές Πιλοτικές Εφαρμογές για τις οποίες προβλέπεται i) να εκπονηθεί χάρτης πορείας δράσεων, ii) συντονισμός δραστηριοτήτων και δράσεων σε όλες τις περιπτωσιολογικές μελέτες, iii) καθοδήγηση και παρακολούθηση της εφαρμογής της δέσμευσης των ενδιαφερόμενων μερών, της αξιολόγησης της ανθεκτικότητας και των πακέτων καινοτομίας, iv) ανάπτυξη και παρακολούθηση Κυρίων Δεικτών Αποτελεσματικότητας, v) ανάπτυξη και συντονισμός των διαδικασιών επικύρωσης για τις δέσμες μέτρων καινοτομίας, vi) παροχή τεκμηριωμένων γνώσεων και συστάσεων σε επίπεδο ΕΕ.

Το Πακέτο Εργασίας 7 επικεντρώνεται στη δημιουργία χαρτοφυλακίου χρηματοδοτικών λύσεων που μπορούν να συμβάλουν συλλογικά στη βελτίωση της ανθεκτικότητας των διαφόρων περιφερειών. Αυτό συνεπάγεται την επίτευξη στόχων όπως η οικονομική ευημερία, η εξάλειψη της ακραίας φτώχειας, η προσαρμογή στην κλιματική αλλαγή, η επιδείνωση της ανθρωπογενούς αύξησης της θερμοκρασίας που εγκρίθηκε στη συμφωνία του Παρισιού. Στην πορεία προς τις βιώσιμες, είναι απαραίτητη μια συστημική προσέγγιση για την αξιοποίηση της συμπληρωματικότητας μεταξύ των διαφόρων πτυχών της πράσινης μετάβασης, με τον προσδιορισμό συνεργειών μεταξύ των ενδιαφερόμενων μερών και των ανταλλαγών μεταξύ των διαφόρων στόχων αειφορίας.

Συγκεκριμένα, τα καθήκοντα του εξωτερικού συνεργάτη περιλαμβάνουν την υποστήριξη στις ακόλουθες δράσεις:

- Πακέτο εργασίας 2: Προσέγγιση καινοτομίας συστημάτων

  - Δράση 2.1: Προσδιορισμός ενδιαφερόμενων μερών και αντιστοίχιση πλαισίου

  - Δράση 2.2: Ανάπτυξη τοπικών δικτύων ARSINOE και έναρξη διαδικασίας συνδημιουργίας

  - Δράση 2.3: Ανάλυση διακυβέρνησης

  - Δράση 2.4: Πρόβλεψη πορειών καινοτομίας για τη συνδημιουργία

  - Δράση 2.5: Δημιουργία περιβάλλοντος εικονικής πραγματικότητας

- Πακέτο εργασίας 5: Σειρά καινοτομιών και συστημάτων υποστήριξης

  - Δράση 5.1 Εργαστήριο αξιολόγησης για τις προτεραιότητες, τις ικανότητες και τα κενά

- Πακέτο εργασίας 6: Μελέτες περιπτώσεων: Δραστηριότητες συντονισμού και εφαρμογής

  - Δράση 6.2: Εφαρμογή της προσέγγισης καινοτομίας συστήματος σε κάθε μελέτη περίπτωσης

  - Δράση 6.3: Εφαρμογή πλαισίου ανθεκτικότητας σε κάθε μελέτη περίπτωσης

  - Δράση 6.4: Ανάπτυξη και επικύρωση πακέτων καινοτομίας σε κάθε μελέτη περίπτωσης

- Πακέτο εργασίας 7: Χρηματοοικονομικά θέματα και χρηματοδοτικά μέσα/ Επιχειρηματικά μοντέλα

  - Δράση 7.1: Συν-δημιουργία οδών για τις ανάγκες χρηματοδότησης και συν-ανάπτυξη χαρτοφυλακίων δυνητικών πηγών χρηματοδότησης

  - Δράση 7.3: Σχεδιασμός χρηματοπιστωτικών μέσων με διαφορετικό βαθμό ωριμότητας και με αποδεκτό επίπεδο κινδύνου

  - Δράση 7.4: Ανάπτυξη υβριδικού μοντέλου χρηματοοικονομικής πληροφόρησης

  - Δράση 7.5: Ανάπτυξη εγχειριδίου για τη βιώσιμη χρηματοδότηση

Παραδοτέα και χρόνος παράδοσης:

Παρακάτω παρουσιάζονται τα παραδοτέα τα οποία θα αναπτυχθούν εντός των δράσεων του έργου καθώς και ο χρόνος παράδοσης τους σύμφωνα με το χρονοδιάγραμμα του έργου, όπως αυτό έχει οριστεί στο Συμφωνητικό Επιχορήγησης:

| Κωδικός Παραδοτέου | Τίτλος Παραδοτέου | Παράδοση |
| --- | --- | --- |
| D.2.1 | Description of stakeholder mapping for case studies | 30/09/2022 |
| D.2.4 | Report on pathways identification in case studies | 30/03/2023 |
| D.5.3 | Overview report on the ARSINOE uptake constracting scheme | 30/09/2025 |
| D.6.6 | Implementation of the System Innovation Approach in all the Case Studies- Final report | 30/06/2025 |
| D.6.7 | Resilience Assessment Implementation for all the Case Studies and evidence-based recommendations for massive resilience at EU level | 30/06/2025 |
| D.6.8 | Innovation packages and financial instruments for all the Case Studies | 30/09/2025 |
| D.7.1 | Pathways of funding requirements and portfolios of potential funding sources | 30/09/2023 |
| D.7.2 | Financial instruments with variant maturities and carrying an acceptable level of risk | 30/09/2024 |
| D.7.3 | Hybrid financial reporting model | 30/03/2024 |
| D.7.4 | Manual on Sustainable Finance | 30/03/2025 |

Οι ανωτέρω ημερομηνίες υποβολής των παραδοτέων υπόκειται σε εκάστοτε αλλαγές σύμφωνα με την πρόοδο υλοποίησης του έργου σε επίπεδο κοινοπραξίας.

### ΔΙΑΡΚΕΙΑ ΣΥΜΒΑΣΗΣ

Οι υπηρεσίες του Συνεργάτη θα παρέχονται από την υπογραφή της σύμβασης έως τις 30/09/2025.

### ΧΡΟΝΟΣ ΚΑΙ ΤΡΟΠΟΣ ΥΠΟΒΟΛΗΣ ΠΡΟΣΦΟΡΑΣ

Καταληκτική ημερομηνία παραλαβής των οικονομικών προσφορών από την Εταιρεία ορίζεται η 05/05/2022 και ώρα 14:00. Ο φάκελος της οικονομικής προσφοράς θα πρέπει να περιλαμβάνει το κόστος των προσφερόμενων υπηρεσιών χωρίς ΦΠΑ. Ο αναλογών ΦΠΑ θα αναγράφεται ξεχωριστά και τα ποσά θα αναγράφονται ολογράφως και αριθμητικώς. Η οικονομική προσφορά θα υποβληθεί σύμφωνα με το επισυναπτόμενο Παράρτημα με τίτλο: ΠΑΡΑΡΤΗΜΑ: ΟΙΚΟΝΟΜΙΚΗ ΠΡΟΣΦΟΡΑ ΕΥΡΩΠΑΪΚΟΥ ΕΡΓΟΥ ARSINOE. Οι προσφορές θα αφορούν ολόκληρο το έργο. Δεν γίνονται δεκτές προσφορές για μέρος των υπηρεσιών.

### ΥΠΟΒΟΛΗ ΦΑΚΕΛΟΥ ΔΙΚΑΙΟΛΟΓΗΤΙΚΩΝ

Κάθε φυσικό ή νομικό πρόσωπο συγχρόνως με την υποβολή της προσφοράς του θα πρέπει να υποβάλλει και τα ακόλουθα επί ποινή αποκλεισμού:

Α) Υπεύθυνη Δήλωση του ν.1599/1986, όπου θα δηλώνει ότι:

- H προσφορά συντάχθηκε σύμφωνα με τους όρους τις παρούσας πρόσκλησης, της οποίας έλαβε γνώση.

- Αποδέχεται ανεπιφύλακτα όλους τους όρους της παρούσας πρόσκλησης και ότι η προσφορά του καλύπτει το σύνολο των ζητούμενων εργασιών.

Β) Απόδειξη εμπειρίας του υποψήφιου Εξωτερικού Συνεργάτη σε δράσεις τουλάχιστον 2 Ευρωπαϊκών έργων κατά τα τελευταία 3 χρόνια, σε σχετικό, με το έργο, αντικείμενο στον τομέα της περιβαλλοντικής βιωσιμότητας και στην συστημική προσαρμογή λιμένων στην κλιματική αλλαγή μέσω σχεδίων δράσης, δημιουργίας συστάδων, υλοποίησης πιλοτικών εφαρμογών και ανάπτυξης νέων τεχνολογιών. Η εμπειρία μπορεί να αποδειχθεί με την υποβολή των σχετικών συμβάσεων.

### ΑΞΙΟΛΟΓΗΣΗ - ΕΠΙΛΟΓΗ ΕΞΩΤΕΡΙΚΟΥ ΣΥΝΕΡΓΑΤΗ

Η αξιολόγηση των προσφορών θα γίνει από την επιτροπή αξιολόγησης της Εταιρείας. Η Επιτροπή Αξιολόγησης επιφυλάσσεται να ζητήσει οποιοδήποτε άλλο έγγραφο κριθεί απαραίτητο. Προσφορές, οι οποίες δεν θα καλύπτουν το σύνολο των απαιτήσεων της παρούσης  θα απορρίπτονται. Κριτήριο επιλογής του Συνεργάτη θα είναι η χαμηλότερη τιμή.

### ΠΑΡΑΛΑΒΗ ΕΡΓΟΥ - ΚΑΤΑΒΟΛΗ ΤΗΣ ΑΜΟΙΒΗΣ

Η παραλαβή του Έργου από τον Συνεργάτη θα γίνεται από την αρμόδια Επιτροπή Παραλαβής της Εταιρείας τμηματικά και σύμφωνα με το χρονοδιάγραμμα που θα εξειδικευθεί στην Σύμβαση μεταξύ του Συνεργάτη και της εταιρείας. Η καταβολή της αμοιβής, θα γίνεται με επιταγή η με μεταφορά σε τραπεζικό λογαριασμό, μετά την έκδοση των σχετικών παραστατικών (Τιμολόγιο Παροχής Υπηρεσιών, φορολογική ενημερότητα) μετά την υπογραφή πρωτοκόλλου παραλαβής και σύμφωνα με το χρονοδιάγραμμα που θα εξειδικευθεί στην Σύμβαση μεταξύ του Συνεργάτη και της εταιρείας. Στην αμοιβή συμπεριλαμβάνονται και δαπάνες για έξοδα ταξιδιών και διαμονής του Συνεργάτη στο εξωτερικό ή και στο εσωτερικό.

### ΥΠΟΧΡΕΩΣΕΙΣ ΤΗΣ ΕΤΑΙΡΕΙΑΣ

Η Εταιρεία υποχρεούται να παράσχει στον Συνεργάτη όλα τα διαθέσιμα σε αυτήν στοιχεία που είναι απαραίτητα για την εκτέλεση της δράσης. Πιο συγκεκριμένα ο συνεργάτης δικαιούται να χρησιμοποιεί τις εγκαταστάσεις και τον εξοπλισμό της εταιρίας συμμετέχοντας στην υλοποίηση της προαναφερθείσας  δράσης, υπό την καθοδήγηση, την εποπτεία και τον έλεγχο των στελεχών της εταιρίας.

### ΥΠΟΧΡΕΩΣΕΙΣ ΣΥΝΕΡΓΑΤΗ

Ο Συνεργάτης θα παρέχει τις υπηρεσίες του υπό την καθοδήγηση του προσωπικού της Εταιρείας και ανάλογα με τις ανάγκες του Έργου οπουδήποτε αυτό απαιτείται και προβλέπεται από την σύμβαση του. Μετά την ολοκλήρωση των παρεχόμενων υπηρεσιών ή την για οποιοδήποτε λόγο λύση της σύμβασης, ο Συνεργάτης οφείλει να επιστρέψει και παραδώσει στην Εταιρεία όλα τα στοιχεία που θα έχουν προκύψει κατά τη χρονική περίοδο ενασχόλησης του και σχετίζονται με το Έργο. Ο Συνεργάτης υποχρεούται να παρίσταται όταν κληθεί προς τούτο, σε υπηρεσιακές συνεδριάσεις (τακτικές και έκτακτες) είτε αυτές πραγματοποιούνται εντός είτε εκτός Ελλάδος, που αφορούν τις υπηρεσίες του και να παρουσιάζει τα απαραίτητα στοιχεία για την αποτελεσματική λήψη αποφάσεων.

Ο Συνεργάτης θα έχει επίσης τις παρακάτω υποχρεώσεις:

- Να ενημερώνει τον ΟΛΠ για την υλοποίηση των ενεργειών και τα χρονοδιαγράμματα

- Να ενημερώνει και επικαιροποιεί το πλάνο εργασιών και των αντίστοιχων υποχρεώσεων βάσει της προόδου του έργου και των αιτημάτων

- Να ανταποκρίνεται στα αιτήματα του ΟΛΠ αναφορικά με την πρόοδο του έργου

- Να διατηρεί όλα τα αρχεία τα οποία παράγει σε ηλεκτρονική μορφή και να είναι άμεσα διαθέσιμα όταν αυτά ζητηθούν

- Να ενημερώνει το σύστημα καταγραφής των τελικών παραδοτέων του έργου (εφ’όσον αυτό είναι διαθέσιμο) και με σχετική περιγραφή καθ’ενός εξ αυτών, αυτά να αναρτώνται στη βάση δεδομένων των παραδοτέων των έργων, που συμμετέχει ο ΟΛΠ.

- Να παρέχει εβδομαδιαία, μηνιαία και ετήσια αναφορά των πεπραγμένων του έργου από μεριάς ΟΛΠ.

- Να χρησιμοποιεί το Ηλεκτρονικό Σύστημα Διαχείρισης του ΟΛΠ, σε ότι αφορά στην διαχείριση και παρακολούθηση προόδου του εν λόγω έργου.

ΕΠΙΣΥΝΑΠΤΕΤΑΙ:

ΠΑΡΑΡΤΗΜΑ: ΟΙΚΟΝΟΜΙΚΗ ΠΡΟΣΦΟΡΑ ΓΙΑ ΤΗΝ ΠΑΡΟΧΗ ΤΕΧΝΙΚΩΝ ΥΠΗΡΕΣΙΩΝ ΓΙΑ ΤΗΝ ΥΛΟΠΟΙΗΣΗ ΤΩΝ ΤΕΧΝΙΚΩΝ ΔΡΑΣΕΩΝ ΤΟΥ ΕΥΡΩΠΑΙΚΟΥ ΕΡΓΟΥ “ARSINOE - Climate resilient regions through systemic solutions and innovations”

ΠΑΡΑΡΤΗΜΑ:

ΠΑΡΑΡΤΗΜΑ: ΟΙΚΟΝΟΜΙΚΗ ΠΡΟΣΦΟΡΑ ΓΙΑ ΤΗΝ ΠΑΡΟΧΗ ΥΠΗΡΕΣΙΩΝ ΓΙΑ ΤΗΝ ΥΛΟΠΟΙΗΣΗ ΤΩΝ ΤΕΧΝΙΚΩΝ ΔΡΑΣΕΩΝ ΤΟΥ ΕΥΡΩΠΑΙΚΟΥ ΕΡΓΟΥ

“ARSINOE - Climate resilient regions through systemic solutions and innovations”

Πειραιάς, .../.../2022

Προς:

ΟΡΓΑΝΙΣΜΟ ΛΙΜΕΝΟΣ ΠΕΙΡΑΙΩΣ Α.Ε.

Ακτή Μιαούλη 10

18538 Πειραιάς

ΘΕΜΑ:  Οικονομική προσφορά για την επιλογή Συνεργάτη από το «Μητρώο Εξωτερικών Συνεργατών για την υλοποίηση Δράσεων Ευρωπαϊκών Έργων και Προγραμμάτων, που συμμετέχει η ΟΛΠ ΑΕ»  με σκοπό την συμμετοχή του στην υλοποίηση των τεχνικών δράσεων του Ευρωπαϊκού έργου “ARSINOE”.

Κύριοι:

Σε συνέχεια της πρόσκλησης για την επιλογή Συνεργάτη από το «Μητρώο Εξωτερικών Συνεργατών για την υλοποίηση Δράσεων Ευρωπαϊκών Έργων και Προγραμμάτων, που συμμετέχει η ΟΛΠ ΑΕ»  με σκοπό την συμμετοχή του στην υλοποίηση των τεχνικών δράσεων του Ευρωπαϊκού έργου “ARSINOE”, σας υποβάλλουμε την οικονομική μας προσφορά ως ακολούθως:

Στοιχεία Προσφέροντος

| Επωνυμία: |  |
| --- | --- |
| Όνομα: |  |
| Επώνυμο: |  |
| Διεύθυνση: |  |
| Τηλέφωνα επικοινωνίας: |  |
| Email: |  |

Οικονομική Προσφορά

Για την επιλογή Συνεργάτη από το «Μητρώο Εξωτερικών Συνεργατών για την υλοποίηση Δράσεων Ευρωπαϊκών Έργων και Προγραμμάτων, που συμμετέχει η ΟΛΠ ΑΕ»  με σκοπό την συμμετοχή του στην υλοποίηση των τεχνικών δράσεων του Ευρωπαϊκού έργου “ARSINOE ”, σας υποβάλλουμε την οικονομική μας προσφορά ως ακολούθως:

| Παραδοτέα |  | Κόστος σε Ευρώ |
| --- | --- | --- |
| D.2.1 | Description of stakeholder mapping for case studies | (Κόστος για το σύνολο των παραδοτέων) |
| D.2.4 | Report on pathways identification in case studies |  |
| D.5.3 | Overview report on the ARSINOE uptake constracting scheme |  |
| D.6.6 | Implementation of the System Innovation Approach in all the Case Studies- Final report |  |
| D.6.7 | Resilience Assessment Implementation for all the Case Studies and evidence-based recommendations for massive resilience at EU level |  |
| D.6.8 | Innovation packages and financial instruments for all the Case Studies |  |
| D.7.1 | Pathways of funding requirements and portfolios of potential funding sources |  |
| D.7.2 | Financial instruments with variant maturities and carrying an acceptable level of risk |  |
| D.7.3 | Hybrid financial reporting model |  |
| D.7.4 | Manual on Sustainable Finance |  |
| Σύνολο χωρίς ΦΠΑ |  |  |
| ΦΠΑ |  |  |
| Σύνολο με ΦΠΑ |  |  |

Με εκτίμηση,

………………………………..

Όνομα - Υπογραφή

|  | PIRAEUS PORT AUTHORITY S.A. Akti Miaouli 10, Piraeus 185 38 |
| --- | --- |

Call of tender with sealed bids

for the selection of an External Expert from the «PPA S.A. External Expert Registry for the implementation of European Projects and Program Activities that PPA S.A. participates» with the purpose of participating in the technical implementation of the European project:

Date of Tender  20/04/2022

## ALL FOR TENDER SUMMARY

| CONTRACTING ENTITY | PIRAEUS PORT AUTHORITY S.A. |
| --- | --- |
| OBJECT OF THE TENDER | Selection of an External Expert from the «PPA S.A. External Expert Registry for the implementation of European Projects and Program Activities that PPA S.A. participates» with the purpose of participating in the technical implementation of the European Project “ARSINOE - Climate resilient regions through systemic solutions and innovations” |
| SERVICE | External Expert Participation in the technical implementation of the European Project “ARSINOE” |
| BUDGET | ______________ |
| DEADLINE FOR BIDS | 05/05/2022 at 14:00 |
| INFORMATION | Procurement@olp.gr |

### PURPOSE OF THE CALL

Selection of an External Expert from the «PPA S.A. External Expert Registry for the implementation of European Projects and Program Activities that PPA S.A. participates» with the purpose of technical implementation of the European Project: “ARSINOE - Climate resilient regions through systemic solutions and innovations”, co-funded by the HORIZON 2020 programme.

### DESCRIPTION OF ARSINOE

ARSINOE intends to be a game-changer for shaping pathways to resilience by delivering regional innovation packages that build an ecosystem to develop and implement innovative climate change adaptation measures and solutions across Europe.

Systems Innovation Approach (SIA) addresses the growing complexity, interdependencies and interconnectedness of modern societies and economies, focusing on the functions of the cross-sectoral system as a whole and on the variety of actors. The Climate Innovation Window (CIW) is the EU reference innovations marketplace for climate adaptation technologies.

ARSINOE shapes the pathways to resilience by bringing together SIA and CIW, to build an ecosystem for climate change adaptation solutions. Within the ARSINOE ecosystem, pathways to solutions are co-created and co-designed by stakeholders, who can then select either existing CIW technologies, or technologies by new providers (or a combination) to form an innovation package. This package may be designed for implementation to a specific region, but its building blocks are transferable and re-usable; they can be re-adapted and updated. In this way, the user (region) gets an innovation package consisting of validated technologies (expanding the market for CIW); new technologies implemented in the specific local innovation package get the opportunity to be validated and become CIW members, while the society (citizens, stakeholders ) benefits as a whole. ARSINOE applies a three-tier, approach:

(a) using SIA it integrates multi-faceted technological, digital, business, governance and environmental aspects with social innovation for the development of adaptation pathways to climate change for specific regions;

(b) it links with CIW to form innovation packages by matching innovators with end-users/regions;

(c) it fosters the ecosystem sustainability and growth with cross-fertilization and replication across regions and scales, at European level and beyond, using specific business models, exploitation and outreach actions.

The ARSINOE approach is show-cased in nine widely varied demonstrators, as a proof-of-concept with regards to its applicability, replicability, potential and efficacy.

### DESCRIPTION OF EXTERNAL EXPERT SERVICES

The purpose of the action is the involvement of the external expert in supporting the participation of PPA in the project “ARSINOE” and the technical implementation of the actions envisaged in the respective Grant Agreement of the project. PPA S.A. participates in the following Work Packages.

In Work Package 2, SIA is in the core of the hereby-suggested methodology for solving complex, multi-parameter problems. Systemic innovation can be seen as an interconnected set of techniques, where each influences the other, with innovation both in the parts of the system and in the ways in which they interconnect. The methods proposed and the ways they interact in the WP2 and with the WP3 and the WP4 is contributing to the innovation approach of ARSINOE. The emphasis is given on the functions of the cross-sectoral system “as a whole” and on the variety of actors, instead of just focusing on specific functions or individual/sectoral benefits. Context and solutions to face climate change will be identified by qualitative analysis in LLs and through interviews and workshops, where the targeted stakeholders and citizens will co-design an accepted vision of the future and set a list of possible pathways to reach their goals.

Work Package 5, focuses in (i) Innovation Bazaar, open tenders for innovations, (ii) development of precise assessment methodologies, selection criteria, (iii) climate window to be chosen in a demand-driven selection, (iv) business models and contracting / market replication (v) forecasting IOT/ market replication

In Work Package 6, there are 9 diverse and complementary Case studies for which the following are envisaged: (i) to develop a roadmap of actions for all the CSs; (ii) to coordinate the activities and actions in all the Case Studies; (iii) to guide and monitor the implementation of the stakeholder engagement, the resilience assessment and the innovation packages for at the CSs throughout the project; (iv) to develop and monitor KPIs; (v) to develop and coordinate the validation procedures for the innovation packages in all the CSs; (vi) to provide evidence-based knowledge and recommendations at EU level.

In Work Package 7, a portfolio of financing solutions will be created that collectively can contribute to the improvement of various regions' resilience. This entails the achievement of goals such as economic prosperity, the eradication of extreme poverty, climate adaptation, the deterioration of anthropogenic warming adopted in the Paris Agreement. On the road to sustainable societies, a systems approach is necessary to exploit the complementarities between different aspects of the green transition identifying synergies among stakeholders and trade-offs between different sustainability objectives.

Specifically, the obligations of the external expert cover the support to the following activities:

- Work Package 2: Systems Innovation Approach

  - Task 2.1: Stakeholder identification and context mapping

  - Task 2.2: Local ARSINOE networks development and co-creation process initiation

  - Task 2.3: Governance analysis

  - Task 2.4: Forecasting innovation pathways co-creation

  - Task 2.5: Virtual Reality environment creation

- Work Package 5: Portfolio of innovations and support schemes

  - Task 5.1 (Self-) Assessment Workshop on Priorities, Capacities and Gaps

- Work Package 6: Case Studies: Coordination and Implementation activities

  - Task 6.2: Implementation of the System Innovation Approach in each Case Study

  - Task 6.3: Resilience framework implementation in each Case Study

  - Task 6.4: Innovation packages development and validation in each Case Study

- Work Package 7: Financial issues and financing instruments/ Business models

  - Task 7.1: Co-creation of pathways of funding requirements and the co-development of portfolios of potential funding sources

  - Task 7.3: Design of financial instruments with variant maturities and carrying an acceptable level of risk

  - Task 7.4: Development of a hybrid financial reporting model

  - Task 7.5: Development of a Manual on Sustainable Finance (M24-M42) Lead: AUEB, participants: all case studies Leaders

Deliverables and Delivery time:

The deliverables that will be developed within the activities of the project and in which the technical expert will contribute, assisting PPA, are presented below, along with their time of delivery in accordance to the schedule set by the consortia in the respective Grant Agreements:

| Deliverable Code | Deliverable Title | Delivery |
| --- | --- | --- |
| D.2.1 | Description of stakeholder mapping for case studies | 30/09/2022 |
| D.2.4 | Report on pathways identification in case studies | 30/03/2023 |
| D.5.3 | Overview report on the ARSINOE uptake constracting scheme | 30/09/2025 |
| D.6.6 | Implementation of the System Innovation Approach in all the Case Studies- Final report | 30/06/2025 |
| D.6.7 | Resilience Assessment Implementation for all the Case Studies and evidence-based recommendations for massive resilience at EU level | 30/06/2025 |
| D.6.8 | Innovation packages and financial instruments for all the Case Studies | 30/09/2025 |
| D.7.1 | Pathways of funding requirements and portfolios of potential funding sources | 30/09/2023 |
| D.7.2 | Financial instruments with variant maturities and carrying an acceptable level of risk | 30/09/2024 |
| D.7.3 | Hybrid financial reporting model | 30/03/2024 |
| D.7.4 | Manual on Sustainable Finance | 30/03/2025 |

The above deadlines are subject to modifications in accordance to the progress of project implementation on a consortium common level.

### DURATION OF CONTRACT

The External Expert Services will be provided from the date of the signature of the contract until 30/09/2025.

### TIME AND METHOD OF SUBMITTING AN OFFER

The closing date for receipt of the financial offers by PPA S.A is: 05/05/2022, at 14:00. The documentation of the financial offer should include the cost of services provided without VAT. The respective VAT will be indicated separately and the amounts will be indicated in words and in figures. The financial offer will be submitted in accordance with the attached Annex entitled: ANNEX: FINANCIAL OFFER FOR THE TECHNICAL IMPLEMENTATION OF THE EUROPEAN PROJECT ARSINOE

The tender offers will refer to the entire requested services. Bids are not accepted for part of the services.

### SUBMISSION OF TENDER DOCUMENTATION

Any natural or legal person shall submit at the same time of submitting his / her bid the following:

Α) A Statutory Declaration of Law 1599/1986, which states that:

- The offer is prepared in accordance with the terms of this call, which the contractor took notice.

- Accepts without limitation all the terms of this call and the offer covers all of the required services.

Β) Proof of experience of the candidate External Expert in actions of at least 2 European projects within the last 3 years, in a relevant, to the project, subject, in the field of environmental sustainability and port adaptation to climate change, through action plans, cluster development, pilot implementation an development of new technologies. The experience can be proved by submitting the relevant contracts.

### EVALUATION - SELECTION OF THE EXTERNAL EXPERT

The evaluation of tender offers will be made by the Company's evaluation committee. The Evaluation Committee reserves the right to request any other necessary document. Offers, which will not cover all the requirements of this call, will be rejected. The external expert selection criterion will be the lowest price.

### ACCEPTANCE OF THE SERVICES DELIVERABLES- PAYMENT OF REMUNERATION

The receipt of the service deliverables from the external expert will be made by the Company's relevant Acceptance Committee in parts, following the relevant Certificate of Delivery and Acceptance and in accordance with the timetable which will be specified in the contract between the External Expert and the company. The payment for the services will be made by check or by transfer to a bank account, after the issuance of the relevant documents (Invoice for Service, Insurance and tax clearance documents) and according to the timetable which will be specified in the contract between the External Expert and the company. The payment of the remuneration includes expenses for the external expert travel and accommodation expenses abroad or in Greece.

### OBLIGATIONS OF THE COMPANY

The Company shall provide the External Expert with all available necessary information for carrying out the services.  More specifically, the External Expert is entitled to use the facilities and equipment of the company in carrying out this action, under the direction, supervision and control of the company executives.

### OBLIGATIONS OF THE EXTERNAL EXPERT

The External Expert will provide his services under the guidance of the Company's personnel and according to the needs of the project, wherever it is required and provided by the contract. Upon completion of the services or upon any other reason of the contract termination, the External Expert must return and deliver to the Company all the data that have arisen during the project period engagement and related to the project. The External Expert is obliged to attend, when invited to do so, at official meetings (ordinary and extraordinary), whether held in or outside Greece, regarding his services in order to present the necessary information for the effective decision-making.

The External Expert will also have the following obligations.

  - To inform PPA on the implementation of actions and timetables

  - Updating the work plan and related obligations based on the progress of the project and the requests

  - Respond to PPA's requests regarding the progress of the project

  - Maintain all the files produced in electronic form and be readily available upon request

  - To update the system for recording the final deliverables of the project and a description of each of them, to be posted in the project deliverables database, in which PPA participates.

  - Provide weekly, monthly and yearly reports of PPA's project activities

  - Use PPA’s Electronic Management System, to what concerns the management and monitoring of progress of the aforementioned project.

ATTACHED:

ANNEX: FINANCIAL OFFER FOR THE PROVISION OF EXTERNAL TECHNICAL SERVICES FOR THE TECHNICAL IMPLEMENTATION OF ΤΗΕ ΕUROPEAN PROJECT “ARSINOE - Climate resilient regions through systemic solutions and innovations”

ANNEX:

FINANCIAL OFFER FOR THE PROVISION OF EXTERNAL TECHNICAL SERVICES FOR THE TECHNICAL IMPLEMENTATION OF ΤΗΕ ΕUROPEAN PROJECT

“ARSINOE - Climate resilient regions through systemic solutions and innovations”

Piraeus, …/.../2022

To:

PIRAEUS PORT AUTHORITY S.A.

Akti Miaouli 10

18538 Piraeus

SUBJECT:  Financial offer for the selection of an External Expert from the «PPA S.A. External Expert Registry for the implementation of European Projects and Program Activities that PPA S.A. participates» with the purpose of providing external technical expertise services for the technical implementation of the European Project “ARSINOE”.

Dear Sirs:

Following the call for tender for the selection of an External Expert from the «PPA S.A. External Expert Registry for the implementation of European Projects and Program Activities that PPA S.A. participates» with the purpose of providing external technical expertise services for the technical implementation of the European Project “ARSINOE”, we hereby submit our financial offer:

Bidder data

| Title: |  |
| --- | --- |
| Name: |  |
| Last name: |  |
| Address: |  |
| Telephones: |  |
| Email: |  |

Financial offer

for the selection of an External Expert from the «PPA S.A. External Expert Registry for the implementation of European Projects and Program Activities that PPA S.A. participates» with the purpose of providing external technical expertise services for the technical implementation of the European Project “ARSINOE”, we submit our financial offer as follows:

| Deliverable |  | Cost in Euro |
| --- | --- | --- |
| D.2.1 | Description of stakeholder mapping for case studies | Cost for the total number of deliverables) |
| D.2.4 | Report on pathways identification in case studies |  |
| D.5.3 | Overview report on the ARSINOE uptake constracting scheme |  |
| D.6.6 | Implementation of the System Innovation Approach in all the Case Studies- Final report |  |
| D.6.7 | Resilience Assessment Implementation for all the Case Studies and evidence-based recommendations for massive resilience at EU level |  |
| D.6.8 | Innovation packages and financial instruments for all the Case Studies |  |
| D.7.1 | Pathways of funding requirements and portfolios of potential funding sources |  |
| D.7.2 | Financial instruments with variant maturities and carrying an acceptable level of risk |  |
| D.7.3 | Hybrid financial reporting model |  |
| D.7.4 | Manual on Sustainable Finance |  |
| Total without VAT |  |  |
| VAT |  |  |
| Total with VAT |  |  |

Sincerely yours,

_________________

Name - Signature